## Sprint Info
Sprint | Screen | Description | P.Start Date | P.End Date | Days | A.Start Date | A.End Date | Status | Remarks
Sprint 1 | Basic | Layer Structure | 2019-12-01 | 2019-12-03 | 2 | 2019-12-01 | 2019-12-03
Sprint 1 | Basic | Login Page | 2019-12-04 | 2019-12-06 | 2 | 2019-12-04 | 2019-12-06
Sprint 1 | Basic | Home Page | 2019-12-07 | 2019-12-09 | 2 | 2019-12-07 | 2019-12-09
Sprint 1 | Basic | API | 2019-12-10 | 2019-12-13 | 3 | 2019-12-10 | 2019-12-13
Sprint 2 | Basic | Tables Structure | 2019-12-14 | 2019-12-15 | 1
Sprint 3 | Setting | Client Config & Mapping | 2019-12-16 | 2019-12-18 | 2
Sprint 3 | Setting | User Config & Mapping | 2019-12-19 | 2019-12-21 | 2
Sprint 3 | Setting | Inventory Column Config & Mapping | 2019-12-22 | 2019-12-24 | 2
Sprint 3 | Setting | Manual Inventory Config & Mapping | 2019-12-25 | 2019-12-27 | 2
Sprint 3 | Setting | Additional Info Config & Mapping | 2019-12-28 | 2019-12-30 | 2
Sprint 3 | Setting | Disposition Config & Mapping & Package | 2020-01-02 | 2020-01-05 | 3
Sprint 3 | Setting | Error Category Config & Mapping & Package | 2020-01-06 | 2020-01-09 | 3
Sprint 3 | Setting | Update Config & Mapping & Package | 2020-01-10 | 2020-01-12 | 2
Sprint 3 | Setting | Guide Config & Mapping & Package | 2020-01-13 | 2020-01-18 | 5
Sprint 4 | Input | Inventory Upload Screen and Package | 2020-01-19 | 2020-01-25 | 6
Sprint 4 | Input | Inventory Auto Upload Console and Package | 2020-01-26 | 2020-01-31 | 5
Sprint 5 | Analysis | Manual Allocation Screen | 2020-02-01 | 2020-02-08 | 7
Sprint 5 | Analysis | Auto Allocation Screen | 2020-02-09 | 2020-02-15 | 6
Sprint 6 | Process | Open Accounts Inbox | 2020-02-16 | 2020-02-21 | 5
Sprint 6 | Process | Assigned Accounts Inbox | 2020-02-22 | 2020-02-25 | 3
Sprint 6 | Process | Manual Accounts Inbox | 2020-02-26 | 2020-03-02 | 5
Sprint 6 | Process | Rework Accounts Inbox | 2020-03-03 | 2020-03-06 | 3
Sprint 6 | Process | Clarification Response Accounts Inbox | 2020-03-07 | 2020-03-12 | 5
Sprint 6 | Audit | Audit Accounts Inbox | 2020-03-13 | 2020-03-18 | 5
Sprint 6 | Audit | ReAudit Accounts Inbox | 2020-03-19 | 2020-03-22 | 3
Sprint 6 | Audit | PreAudit Accounts Inbox | 2020-03-23 | 2020-03-26 | 3
Sprint 6 | Audit | Rebuttal Accounts Inbox | 2020-03-27 | 2020-04-01 | 5
Sprint 6 | Audit | Clarification request Accounts Inbox | 2020-04-02 | 2020-04-05 | 3
Sprint 7 | Process | Priority Accounts Inbox | 2020-04-06 | 2020-04-09 | 3
Sprint 7 | Process | Analyst Accounts Inbox | 2020-04-10 | 2020-04-13 | 3
Sprint 7 | Process | Caller Accounts Inbox | 2020-04-14 | 2020-04-17 | 3
Sprint 7 | Process | Supporter Accounts Inbox | 2020-04-18 | 2020-04-21 | 3
Sprint 7 | Process | Coder Accounts Inbox | 2020-04-22 | 2020-04-25 | 3
Sprint 7 | Process | Letter Packer Accounts Inbox | 2020-04-26 | 2020-04-29 | 3
Sprint 8 | OutPut | Reports | 2020-04-30 | 2020-05-10 | 10
Sprint 9 | OutPut | Dashboard in Power BI | 2020-05-11 | 2020-05-21 | 10
Sprint 10 | Basic | Security Level & Publish | 2020-05-22 | 2020-05-31 | 9
Formulas:
P.End Date = +[P.Start Date]+2
A.End Date = +[A.Start Date]+[Days]